## Sheet1
Table 6‑7: Implementation schedule of Hanthana Wewa restoration
Item | Duration (Months)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Survey and Investigation
Designs and estimation
Burrow area investigation
Procurement and awarding
Structural concrete work and gates
Earthwork, riprap, and site clearing