## Sheet1
Table 6‑8: Implementation schedule of TSHDA Tank
Item | Duration (Months)
| 1 | 2 | 3 | 4 | 5 | 6
Survey and Investigation
Designs and estimation
Burrow area investigation
Procurement and awarding
Structural concrete work and gates
Earthwork, riprap, and site clearing