## Sheet1
Table 6 12: Time frame for implementing domestic water and water source protection
Duration (Months)
Implementation Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Survey and estimation for water supply schemes
Ratification for proposals
Procurement procedure and selection of a builder
Construction
Quality Assurance
Certificate of Completion, Taking Over & Settlement of payments