## Table 6‑42
Table 6 42: Timeframe for the implementation
| Activities | 2024 Maha | 2025 Yala | 2025 Maha | 2026 Yala | 2026 Maha | 2027 Yala | Responsibility | Supervision
1 | Supporting the Export of agricultural crops
1.1 | Identification of farmers and conducting basic awareness on cultivation of export agriculture crops | [6 empty] | MDMWPC/ EO | AD (P)
1.2 | Make Initial arrangement with DEA for the supply of Plants. | [6 empty] | AD (P) | DS
1.3 | Supply and distribution of plants (Coffee, Pepper, Vanilla, Clove, Ginger) | [6 empty] | EO (DEA) | AD (P)
1.4 | Conducting awareness quality improvement and minimizing post-harvest losses | [6 empty] | EO | ADO
1.5 | Monitoring and supervision | [6 empty] | MDMWPC | EO (DEA)
2 | Supporting paddy cultivation
2.1 | Identification and signing of MoU with selected farmers | [6 empty] | MDMWPC | ADO
2.2 | Conducting basic awareness of the “Parachute method” | [6 empty] | AI | ADO/AD (P)
2.3 | Arranging of farmers contribution (50% of the cost) | [6 empty] | MDMWPC | AD (P)
2.4 | Supply and distribution of seed planting trays | [6 empty] | ADO | AD (P)
2.5 | Monitoring and supervision | [6 empty] | MDMWPC | AI
3 | Supporting the protection of crops from animals
3.1 | Identification and signing of MoU with selected farmers | [6 empty] | MDMWPC | ADO
3.2 | Conduct awareness on agricultural crop protection from wild animals | [6 empty] | AI | ADO
3.3 | Arranging of farmer contribution (50% of the cost) | [6 empty] | MDMWPC | ADO/AD (P)
3.4 | Supply and distributions of electric fence (Viduli Pambaya) | [6 empty] | ADO | AD (P)
3.5 | Monitoring and supervision | [6 empty] | MDMWPC | AI
4 | Implementation of protected agricultural methods (polytunnel)
4.1 | Identification and signing of MoU with selected farmers | [6 empty] | AI | AD (P)
4.2 | Conduct awareness on protected agriculture | [6 empty] | TO | AI
4.3 | Arranging of farmer contribution (50% of the cost) | [6 empty] | MDMWPC | AI/AD (P)
4.4 | Supply and distribution of polytunnel | [6 empty] | AI | AD (P)
4.5 | Monitoring and supervision | [6 empty] | MDMWPC | AI
5 | Supporting fruit cultivation (Banna, Mango, Avocado)
5.1 | Identification of farmers and conducting basic awareness of cultivation | [6 empty] | MDMWPC/ AI | ADO
5.2 | Land preparation for cultivation | [6 empty] | Beneficiaries | AI
5.3 | Supply and distribution of fruit plants to the farmers | [6 empty] | ADO | AD (P)
5.4 | Monitoring and supervision | [6 empty] | MDMWPC | AI
6 | Introducing value addition and new technology
6.1 | Identification and signing of MoU with selected farmers/ producers | [6 empty] | MDMWPC | AD (P)
6.2 | Conducting basic awareness on processing | [6 empty] | Supplier/ Line agency | AD (P)
6.3 | Supply and distribution of the following machines and Equipment to the farmers and producers - Black pepper-making machines (Balancing kit), White pepper production machines, Curry powder grinding, Jackfruit drying machines, Alimana chopper machines, and Ginger slicing machines. Areca nut slicing machines, Incubator (Chick hatching) | [6 empty] | AD (P) | DS
6.4 | Monitoring and supervision | [6 empty] | MDMWPC | AD (P)
7 | Supporting animal husbandry
7.1 | Identification and signing of MOU with selected farmers | [6 empty] | MWMC/LDI | Vet. Surgeon
7.2 | Conducting basic awareness programs | [6 empty] | LDI | Vet. Surgeon
7.3 | Supply and providing of suitable animals - Cows, Goat, Chicks | [6 empty] | Vet. Surgeon | DS
7.4 | Providing support to construction of sheds, Sheds – cow, Sheds – goat | [6 empty] | Vet. Surgeon | DS
7.5 | Monitoring and supervision | [6 empty] | MDMWPC | LDI
8 | Supporting vegetable cultivation
8.1 | Identification of farmers and conducting basic awareness on cultivation | [6 empty] | MDMWPC/ AI | ADO
8.2 | Supply and distribution of vegetable seeds (Capsicum, Cabbages, Green Chili, Beans, Tomato) | [6 empty] | ADO | ADO
8.3 | Conducting awareness on minimizing of post-harvest losses | [6 empty] | EO/AI | ADO
8.4 | Monitoring and supervision | [6 empty] | MDMWPC | AI