## Sheet1
Table 6‑13: Cost estimate of minor irrigation related proposals with locations
GND | Scheme/Name | Problem to be addressed/ Need | Coordinates |  | Recommended Remedial Actions | Estimated Cost
946 | Ududampala anicut | Anicut restoration need | 7.246 | 80.6486 | 1. Chip off weathered concrete surfaces 2. Drill, fix and grout 16mm dia "T " shape dowels at 500mm intervals 3. Apply grade 25 concrete 125mm thick curtaining 4. Provide anicut planks | 600000
946 | Ududampala canal | Reservation, repairs & Backfilling | 7.246 | 80.6486 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length of about 200 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 174000
946 | Uda-assadduma canal | Reservation, repairs & Backfilling | 7.246 | 80.645 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length of about 200 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 174000
946 | Rankiriyagolla anicut | Anicut gate refurbishment | 7.2473 | 80.6448 | Remove perished gates and provide new components | 150000
946 | Rankiriyagolla canal (1) | Reservation, repairs & Backfilling | 7.2473 | 80.6449 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 87000
946 | Rankiriyagolla canal (2) | Reservation, repairs & Backfilling | 7.2489 | 80.6456 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 87000
946 | Rankiriyagolla canal (3) | Reservation, repairs & Backfilling | 7.2495 | 80.6465 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 87000
946 | Palle-assadduma canal | Reservation, repairs & Backfilling | 7.2461 | 80.6453 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 87000
947 | Diddeniya Oya | Reservation, tree planting | 7.2478 | 80.6435 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 109700
948 | Kebalewa canal | Leaks in the canal. | 7.1517 | 80.3908 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 87000
948 | Kebalewa canal | Leaks in the canal. | 7.1517 | 80.3996 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 87000
948 | Kebalewa canal | Leaks in the canal. | 7.1514 | 80.3821 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 87000
948 | Kebalewa canal | Leaks in the canal. | 7.1514 | 80.3821 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 87000
948 | Kebalewa canal | Leaks in the canal. | 7.1318 | 80.3819 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 87000
948 | Kebalewa canal | Upstream embankment collapse and retaining wall required | 7.1517 | 30.3908 | Provide 15m long x2m high RCC retaining wall | 400000
948 | Kebalewa canal | Leaks in the canal. | 7.1318 | 80.3919 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 87000
948 | Kalaldora canal | Leaks in the canal. | 7.1515 | 80.3974 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 87000
948 | Kalaldora canal | Leaks in the canal. | 7.1514 | 80.3977 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 87000
948 | Kalaldora canal | Leaks in the canal and overflow | 7.1519 | 80.3913 | Demolish and reconstruct 125mm thick , 0.4m wide and 0.5m high and 100m long canal with grade 25 concrete -single banking | 690000
948 | Kalaldora canal | Leaks in the canal and overflow | 7.1514 | 80.3995 | Demolish and reconstruct 125mm thick , 0.4m wide and 0.5m high and 100m long canal with grade 25 concrete -single banking | 690000
948 | Kalaldora canal | Leaks in the canal and overflow | 7.1515 | 80.3911 | Demolish and reconstruct 125mm thick , 0.4m wide and 0.5m high and 100m long canal with grade 25 concrete -single banking | 690000
948 | Kalaldora canal | Remove rock obstacles | 7.1514 | 80.3995 | Manually drill 20-25 dia holes @300mm interval and apply expansive mortar | 40000
948 | Kalaldora canal | Leaks in the canal and overflow | 7.1516 | 80.3912 | Demolish and reconstruct 125mm thick , 0.4m wide and 0.5m high and 100m long canal with grade 25 concrete -single banking | 690000
948 | Kalaldora canal | Leaks in the canal and overflow | 7.1516 | 80.3913 | Demolish and reconstruct 125mm thick , 0.4m wide and 0.5m high and 100m long canal with grade 25 concrete -single banking | 690000
948 | Kalaldora canal | Leaks in the canal and overflow | 7.1515 | 80.3919 | Demolish and reconstruct 125mm thick , 0.4m wide and 0.5m high and 100m long canal with grade 25 concrete -single banking | 690000
948 | Bulathgamuwa canal | Concrete lining to be repaired | 7.1515 | 80.3915 | Demolish and reconstruct 100mm thick , 0.4m wide and 0.3m high and 100m long canal with grade 25 concrete -single banking | 500000
948 | Bulathgamuwa canal | Concrete lining to be repaired | 7.1513 | 80.3921 | Demolish and reconstruct 100mm thick , 0.4m wide and 0.3m high and 100m long canal with grade 25 concrete -single banking | 500000
948 | Kahatagahamula canal | Retaining wall is required | 7.4586 | 80.3914 | Provide 15m long x2m high RCC retaining wall | 400000
948 | Kahatagahamula canal | Canal leak/earth filling need | 7.115 | 80.3914 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 87000
948 | Kahatagahamula canal | Canal leak/earth filling need | 7.1549 | 80.3914 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface | 87000
948 | Kahatagahamula canal | Canal leak/earth filling need | 7.1546 | 80.3916 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 87000
948 | Kahatagahamula canal | Canal leak/earth filling need | 7.1511 | 80.1661 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 87000
948 | Thelabu pallewaththa | Canal leak/earth filling need | 7.146 | 80.3912 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 87000
948 | Thelabu pallewaththa | Canal leak/earth filling need | 7.1547 | 80.3991 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 87000
948 | Thelabu pallewaththa | Canal leak/earth filling need | 7.1558 | 80.3912 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 87000
948 | Thelabu pallewaththa | Canal leak/earth filling need | 7.1579 | 80.3913 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 87000
948 | Ginithulawa canal | Canal leak/earth filling need | 7.1597 | 80.3971 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 87000
948 | Ginithulawa canal | Canal leak/earth filling need | 7.1596 | 80.3974 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 87000
948 | Ginithulawa canal | Canal leak/earth filling need | 7.1599 | 80.3987 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 87000
948 | Bogahagoda canal | Anicut leaks and unserviceable | 7.1574 | 80.3929 | Demolish and reconstruct the anicut | 700000
948 | Bogahagoda canal | Remove rock obstacles | 7.1075 | 80.4032 | Manually drill 20-25 dia holes @300mm intervals and apply expansive mortar | 40000
948 | Kikawula Canal | Canal leak/earth filling need | 7.1554 | 80.3923 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 87000
948 | Kikawula Canal | Canal leak/earth filling need | 7.1545 | 80.3936 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 87000
948 | Pihillewaththa canal | Need overhead pipe or conduit with drainage undercrossing | 7.1586 | 80.3922 | Construct 125mm thick, 0.4m wide and 0.4m high and 50m long grade 25 RCC trough on piers | 1400000
950 | Thalagolla Kekiriyawela canal | Canal damaged due to earth slip | 7.2505 | 80.654 | Construct 125mm thick, 0.4m wide, and 0.4m high and 90m long concrete canal -double banking | 1210000
950 | Thalagolla Kekiriyawela canal | Need re-construction of decayed concrete lining | 7.2516 | 80.6556 | Demolish and reconstruct 125mm thick, 0.4m wide, and 0.5m high and 100m long canal with grade 25 concrete -single banking | 690000
950 | Kekiriyawela anicut | Need rehabilitation | 7.2505 | 80.654 | Provide 100 mm thick grade 25 concrete curtain after chipping the weathered surface | 450000
950 | Iththagahalanda canal | canal earthwork and reservation are need | 7.2483 | 80.6565 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 87000
950 | Canal below the playground | Drainage under crossing is required | 7.2511 | 80.6572 | Construction of a garbage trap using 600mm dia concrete pipes and a GI gabion box cage. | 87000
953 | Hommare canal | no reservation & seepage in earthen bunds | 7.2595 | 80.6503 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 200 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 87000
955 | Booge canal | No reservation boundary | 7.1511 | 80.375 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 261000
955 | Booge canal | Canal erosion near the anicut. | 7.1511 | 80.375 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length of about 200 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Plant two rows of areca nut trees and mixed dense plantation of Mee, Kumbuk, Godapara, Kekuna, etc., for 5m wide and 10m long reservation areas. | 174000
955 | Gorakagahamadiththa | Need d/s retaining wall | 7.1512 | 80.3855 | Provide 15m-20m long RCC retaining wall | 500000
955 | Amba kumbura canal | Erosion of canal embankment | 7.1512 | 80.3849 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 261000
955 | Dungahamula canal | No reservation boundary | 7.1512 | 80.3835 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length of about 200 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface | 174000
955 | Dungahamula canal | Need drainage under crossing | 7.1512 | 80.3842 | Construction of an undercrossing structure with a garbage trap using 600mm dia concrete pipes and a GI gabion box cage. | 106000
955 | Dungahamula canal | Canal seepage: debris trap need | 7.1513 | 80.3842 | Construction of a garbage trap using 600mm dia concrete pipes and a GI gabion box cage. | 53000
955 | Dungahamula canal | Need drainage under crossing | 7.1514 | 80.3842 | 1. Earth filling of 3m wide and length about 50 m area. 2. Construction of a garbage trap using 600mm dia concrete pipes and a GI gabion box cage. | 140000
962 | Thibbotuwawe canal | weak L/B Embankment need earth fill | 7.2519 | 80.6627 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface | 87000
962 | Thibbotuwawe canal | Siltation: Need silt ejector | 7.2528 | 80.663 | Construct a silt ejector with a downstream gate | 200000
962 | Thibbotuwawe canal | Canal leaks need concreting | 7.2517 | 80.6669 | Demolish and reconstruct a 100mm thick, 0.4m wide and 0.3m high and 100m long canal with grade 25 concrete -single banking | 500000
962 | Thibbotuwawe canal | weak L/B Embankment need earth fill | 7.2523 | 80.6654 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length of about 200 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 174000
962 | Imbulhitiyawa canal | weak L/B Embankment, need earth fill | 7.1592 | 80.3952 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length of about 200 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface | 174000
962 | Imbulhitiyawa canal | Canal damage due to overflow, need canal spill | 7.1591 | 80.3959 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface | 87000
962 | Imbulhitiyawa canal | weak L/B Embankment, need earth fill & retaining wall | 7.1576 | 80.4621 |  | 348000
964 | Uuranheramula Anicut | No d/s reservation of the canal. | 7.243 | 80.6551 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length of about 200 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 174000
964 | Uuranheramula Anicut | damaged anicut planks | 7.1423 | 80.3911 | Provide anicut planks | 40000
964 | Uuranheramulla canal | Leaks in the canal | 7.2415 | 80.6545 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length about 100 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface | 87000
964 | Middle canal | No d/s reservation of the canal. | 7.1426 | 80.391 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length of about 200 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface. | 174000
964 | Feeder Canal | Leaks in the canal | 7.1422 | 80.3595 | 1. Earth filling to narrow tracks to form channel bund of 1 - 1.5m wide and length of about 200 m. 2. Protection by turfing sods with vetiver grass rows. or 3. Cultivate edible varieties such as Mukunuwenna, Gotukola, and Thampala along the incline surface | 174000
| Total |  |  |  |  | 18054700