## MWS-003
Table 6‑1: Key activities proposed for soil and water conservation in MWS-003
No. | GND No. | GN Division | Key Activities proposed for Soil and Water conservation | Priority based on Soil Erosion Hazard | Sub Item No. | N or X | E or Y | Quantity | Proposed measure/s | Uniti Cost (Rs.) | Total Cost (Rs.) | Total Cost | Contribution (Local Community, LA, and the project) | Time frame for the implementation
1 | 946 | Uduwela Udagama East | 1. Rennovation of Ududampala Kandura as a Leader Drain/Main Drain | 2 | 1 | 7.246 | 80.6485 | 4 km | Clearing and planting some trees along the banks (Areca nut) and other conservation practices |  | 400000 |  | Labour and other basic services by the Local community/ Shramadana | 0.5 Years
|  |  | 2. Establishing a Retaining Wall - Near Mr. Sunil Premathilake's house, 40° | 4 | 1 | 7.2456 | 80.6472 | 30 m x 3 m | Retaining Wall using stones | 2,000.00 m-2 | 180000 |  | Funds by the Project | 0.25 Years
|  |  | 3. Establishing a Retaining Wall - Community Center, Udagama, 60° | 3 | 1 | 7.2458 | 80.646 | 6 m x 9 m | Retaining Wall using stones | 2,000.00 m-2 | 108000 |  | Funds by the Project | 0.25 Years
|  |  | 4. Establishing a Retaining Wall at Hanthana Temple Road, 60° | 4 | 1 | 7.2422 | 80.6408 | 10 m x 4 m | Retaining Wall/Side Wall of the bridge | 2,000.00 m-2 | 80000 |  | Funds by the Project | 0.25 Years
|  |  | 5. Establishing a Retaining Wall near Udakanda Sangaraja Senasanaya, 50° | 3 | 1 | 7.2351 | 80.637 | 3 m x 5 m | Retaining Wall using stones | 2,000.00 m-2 | 30000 |  | Funds by the Project | 0.25 Years
|  |  | 6. Rennovation of Leader Drain/Kandura along the road to Devalaya, 65° | 1 | 1 | 7.2372 | 80.6376 | 1 km | Clearing and planting some trees along the banks (Areca nut) and other conservation practices |  | 100000 |  | Labour and other basic services by the Local community/ Shramadana | 0.5 Years
|  |  | 8. Stone terracing the stair case near Udagama Welfare Society/Community Center | 1 | 1 | 7.2467 | 80.6435 | 0.15 m x 1.5 m x 1 m | Stone terracing | 2,500.00 m-1 | 562500 | 1460500 |  | 0.25 Years
2 | 947 | Uduwela Udagama West | 1. Rennovation of eight (8) Leader Drains | 5 | 1 | 7.24951, 7.24935 | 80.64201, 90.63963 | 10.1 km | Clearing and planting some trees along the banks (Areca nut) and other conservation practices |  | 1010000 |  | Labour and other basic services by the Local community/ Shramadana | 1 Year
|  |  |  | 1 | 2 | 7.2484 | 80.6396
|  |  |  | 5 | 3 | 7.24571, 7.24694, 7.24807 | 80.63496, 80.63465, 80.63402
|  |  |  | 1 | 4 | 7.2496 | 80.6338
|  |  |  | 4 | 5 | 7.2497 | 80.6322
|  |  |  | 4 | 6 | 7.2508 | 80.6419
|  |  |  | 4 | 7 | 7.2502 | 80.6381
|  |  |  | 4 | 8 | 7.1449 | 80.3811
|  |  | 2. Soil and mointure conservation measures in Ellenakumbura Home Garden, 25° | 1 | 1 | 7.2487 | 80.6434 | 2 ha | Lock and spills Live fencing/SALT | 400.00 m-1 250.00 m-1 | 800000.00 500000.00 |  | Guidance by NRMC Funds by the Project | 0.25 Years
|  |  | 3. Soil and moisture conservation measures in Ethulgama Upalihimi Shri Sobhitharamaya, 60° | 1 | 1 | 7.2525 | 80.6401 | 1 ha | Live fencing/SALT | 250.00 m-1 | 250000 |  | Funds by the Project | 0.25 Years
|  |  | 4. Soil and moisture conservation measures in Udagama, already cultivated, 60° | 1 | 1 | 7.2471 | 80.6423 | 0.1 ha | Live fencing/SALT | 250.00 m-1 | 2500 |  | Funds by the Project | 0.25 Years
|  |  | 5. Establishing a Retaining Wall with stones Uduwela, Diddeniya (Upper) | 5 | 1 | 7.2471 | 80.6427 | 6 m x 7.5 m | Retaining Wall using stones | 2,000.00 m-2 | 90000 |  | Funds by the Project | 0.25 Years
|  |  | 6. Establishing a Retaining Wall with stones, Ellana Kumbura Road, 70° | 3 | 1 | 7.2486 | 80.643 | 15 m x 6 m | Retaining Wall using stones | 2,000.00 m-3 | 180000 | 3082500 | Funds by the Project | 0.25 Years
3 | 948 | Uduwela Pallegama South | 1. Establishing a Retaining Wall with stones/Water Source at the land of Mr. Karunapala, 30° | 2 | 1 | 7.1524 | 80.0525 | 25 m x 0.5 m | Retaining Wall using stones | 2,000.00 m-2 | 25000 |  | Labour and other basic services by the Local community/ Shramadana | 0.25 Years
|  |  | 2. Rennovation of Leader Drain/Akkaragala Kandura, Mrs. Gnanawathi | 4 | 1 | 7.1519 | 80.3915 | 450 m | Clearing and planting some trees along the banks (Areca nut) and other conservation practices |  | 45000 |  | Labour and other basic services by the Local community/ Shramadana | 0.25 Years
|  |  | 3. Establishing a soil bund | 3 | 1 | 7.152 | 80.3912 | 80 m | Soil Bund | 400.00 m-1 | 32000 |  | Funds by the Project | 0.25 Years
|  |  | 4. Soil and water conservation measures in the land of Mrs. N.K.G. Leelawathi, 25° | 1 | 1 | 7.1517 | 80.3997 | 2.5 ha | Lock and spills Live fencing/SALT | 400.00 m-1 250.00 m-1 | 1000000.00 625000.00 |  |  | 0.25 Years
|  |  | 5. Soil and water conservation at the land of Mr. Herbert Jayasinghe, 65° | 4 | 1 | 7.1519 | 80.3913 | 1.5 ha | Live fencing/SALT | 250.00 m-1 | 375000 |  | Funds by the Project | 0.25 Years
|  |  | 6. Soil and water conservation at the land of Mr. Siri Sugath Ranasinghe, 70° | 3 | 1 | 7.1518 | 80.3913 | 0.5 ha | Live fencing/SALT | 250.00 m-1 | 125000 |  | Funds by the Project | 0.25 Years
|  |  | 7. Soil and water conservation at the lands of Akaragala (Middle), 65° | 1 | 1 | 7.15188, 7.15151 | 80.39123, 80.39107 | 2 ha | Live fencing/SALT | 250.00 m-1 | 500000 |  | Funds by the Project | 0.25 Years
|  |  | 8. Soil and water conservation at the lands of other, 75° | 1 | 1 | 7.1519 | 80.3914 | 1 ha | Live fencing/SALT | 250.00 m-1 | 250000 | 2977000 | Funds by the Project | 0.25 Years
4 | 949 | Uduwela Pallegama East | 1. Rennovation of Kekiriwela Leader Drain (Pitale) | 3 | 1 | 7.2519 | 80.6603 | 100 m | Clearing and planting some trees along the banks (Areca nut) and other conservation practices |  | 100000 |  | Labour and other basic services by the Local community/ Shramadana | 0.25 Years
|  |  | 2. Soil and water conservation in Kekiriwela, 90° | 1 | 1 | 7.249 | 80.6591 | 10 ha | Live fencing/SALT Maintaining aforest cover or Planting perenial crops such as pepper, coffee etc. | 250.00 m-1 | 2500000 |  | Labour and other basic services by the Local community/ Shramadana Funds by the Project | 0.5 Years
|  |  | 3. Soil and water conservation in Mudunepara (Home garden), 85° | 5 | 1 | 7.2502 | 80.658.34 | 14 ha | Live fencing/SALT Planting perenial crops such as pepper, coffee etc. Stone terracing/lock and spills, as applied | 250.00 m-1 | 3500000 |  | Funds by the Project | 1 Year
|  |  | 4. Establishing a Retaining Wall at G.B.G. Siriya, Kekiriwela/Ethulgama Weldambala | 1 | 1 | 7.146 | 80.3935 | 0.3 km x 3 m | Retaining Wall using stones | 2,000.00 m-2 | 1800000 |  | Funds by the Project | 0.25 Years
|  |  | 5. Establishing a Retaining Wall at G.B.G.Dhanapala, Kekiriwela/Ethulgama Weldambala | 1 | 1 | 7.2499 | 80.6602 | 0.3 km x 3 m | Retaining Wall using stones | 2,000.00 m-3 | 1800000 | 9700000 | Funds by the Project | 0.25 Years
5 | 950 | Uduwela Pallegama West | 1. Rennovation of Leader Drain close to Weldambala Dharmapala School | 5 | 1 | 7.25109, 7.25137, 7.25135 | 80.65724, 80.65721, 80. 65619 | 600 m | Clearing and planting some trees along the banks (Areca nut) and other conservation practices |  | 60000 |  | Labour and other basic services by the Local community/ Shramadana | 1 Year
|  |  | 2. Rennovation of Leader Drain added to Thelabu Oya | 2 | 1 | 7.2497 | 80.6542 | 5 km | Clearing and planting some trees along the banks (Areca nut) and other conservation practices |  | 500000 |  | Labour and other basic services by the Local community/ Shramadana | 1.5 Years
|  |  | 3. Improving drainage facility of Galpoththa Hena Road | 1 | 1 | 7.2491 | 80.6562 | 0.6 km x 0.5 m x 0.5 m | Drains | 3,000.00 m-3 | 450000 |  | Labour and other basic services by the Local community/ Shramadana | 0.25 Years
|  |  | 4. Soil and water conservation in lands near Galpoththa Hena Road (35°) | 3 | 1 | 7.2508 | 80.6567 | 4 ha | Lock and spills | 400.00 m-1 | 1600000 |  |  | 1 Year
|  |  | 5. Development of Kalagolla Road (Middle of the village)/Building up of stone layered drain | 2 | 1 | 7.2502 | 80.6547 | 0.25 km x 0.5 m x 0.5 m | Drains | 3,000.00 m-3 | 187500 |  | Labour and other basic services by the Local community/ Shramadana | 0.25 Years
|  |  | 6. Homegarden neer Beerawala Oya, 70°, | 1 | 1 | 7.2488 | 80.6536 | 0.4 ha | Live fencing/SALT Stone terracing, as applied | 250.00 m-1 | 100000 |  | Labour and other basic services by the Local community/ Shramadana | 0.5 Years
|  |  | 7. A Leader Drain with a culvert for the home garden at Nagahalanda, 45°, 3 ac land | 2 | 1 | 7.2484 | 80.6544 | 100 m | Clearing and planting some trees along the banks (Areca nut) and other conservation practices |  | 10000 | 2907500 | Labour and other basic services by the Local community/ Shramadana | 0.25 Years
6 | 951 | Ratemulla | 1. Soil and water conservation measures in 'Janaudanaya', Hanthana Rajamaha Viharaya, 20° | 2 | 1 | 7.2454 | 80.6487 | 6 ha | Lock and spills Live fencing/SALT | 400.00 m-1 250.00 m-1 | 2400000 1500000 |  | Labour and other basic services by the Local community Guidance by NRMC | 0.5 Years 0.25 Years
|  |  | 2. Establishing four (04) Retaining Walls (25 m x 4), 7.5 m height | 3 | 1 | 7.2458 | 80.6485 | 100 m x 7.5 m | Retaining Wall using stones | 2,000.00 m-2 | 1500000 |  | Funds by the Project | 0.5 Years
|  |  | (W.G. Premadasa, W.G. Dayavansha, O.W. Sumith Kumara and N.K. Jayasinghe) | 2 | 2 | 7.246 | 80.6483 | [5 empty] | Labour and other basic services by the Local community
|  |  |  | 2 | 3 | 7.2454 | 80.6487
|  |  |  | 3 | 4 | 7.2424 | 80.648 |  |  |  |  | 5400000
7 | 952 | Monarangala | 1. Rennovation of twelve (12) Leader Drains | 1 | 1 | 1026938 | 6244129 | 56 km | Clearing and planting some trees along the banks (Areca nut) and other conservation practices |  | 5600000 |  | Labour and other basic services by the Local community/ Shramadana | 2 Years
|  |  |  | 2 | 2 | 1027094 | 6244117
|  |  |  | 2 | 3 | 1027148 | 6244109
|  |  |  | 2 | 4 | 1027244 | 6244105
|  |  |  | 2 | 5 | 1027287 | 6244074
|  |  |  | 2 | 6 | 1027264 | 6243713
|  |  |  | 2 | 7 | 1027454 | 6244067
|  |  |  | 2 | 8 | 1027525 | 6244036
|  |  |  | 2 | 9 | 1027647 | 6244017
|  |  |  | 2 | 10 | 1027772 | 6244000
|  |  |  | 2 | 11 | 1027811 | 6243983
|  |  |  | 2 | 12 | 1027882 | 6243991
|  |  | 2. Retaining Wall 1 (New Dodamgahawatte) | 1 | 1 | 1027005 | 6244086 | 75 m x 4 m | Retaining Wall using stones | 2,000.00 m-2 | 600000 |  | Guidance by NRMC | 0.25 Years
|  |  | 3. Retaining Wall 2 (Silverthenne Community Center) | 5 | 1 | 1027522 | 6244088 | 60 m x 5 m | Retaining Wall using stones | 2,000.00 m-2 | 600000 | 6800000 | Funds by the Project | 0.25 Years
8 | 953 | Wathuliyadda | 1. Rennovation of ten (10) Leader Drains | 1 | 1 | 7.1539 | 80.3951 | 11.5 km | Clearing and planting some trees along the banks (Areca nut) and other conservation practices |  | 1150000 |  | Labour and other basic services by the Local community | 2 Years
|  |  |  | 5 | 2 | 7.1539 | 80.3978
|  |  |  | 3 | 3 | 7.1539 | 80.3913
|  |  |  | 3 | 4 | 7.1546 | 80.3978
|  |  |  | 5 | 5 | 7.1545 | 80.3996
|  |  |  | 5 | 6 | 7.16 | 80.3952
|  |  |  | 5 | 7 | 7.1546 | 80.3935
|  |  |  | 1 | 8 | 7.1543 | 80.594
|  |  |  | 2 | 9 | 7.1541 | 80.3856
|  |  |  | 2 | 10 | 7.1542 | 80.3852
|  |  | 2. Soil and water conservation in Ginihiriyawaththe/Home Garden, 70° | 5 | 1 | 7.1545 | 80.3977 | 10 ha | Live fencing/SALT Stone terracing/lock and spills, as applied | 250.00 m-1 | 2500000 |  | Labour and other basic services by the Local community | 0.5 Years
|  |  | 3. Soil and water conservation in Wathuliyadda/Home Garden, 65° | 3 | 1 | 7.1539 | 80.3853 | 3 ha | Live fencing/SALT Stone terracing/lock and spills, as applied | 250.00 m-1 | 750000 |  | Labour and other basic services by the Local community | 0.25 Years
|  |  | 4. Wewekele Imbulathenna/Home Garden, 85°/85°/90° | 5 | 1 | 7.15476271, 7.1545767, 7.1546460 | 80.64778, 80.3852, 80.3852921 | 15 ha | Live fencing/SALT Stone terracing/lock and spills, as applied | 250.00 m-1 | 3750000 |  | Labour and other basic services by the Local community | 0.5 Years
|  |  | 5. Stone terracing in N. Premachandra, Wathuliyadda, 70° | 1 | 1 | 7.1543 | 80.3907 | 0.5 ha | Live fencing/SALT | 250.00 m-1 | 125000 |  | Labour and other basic services by the Local community | 0.25 Years
|  |  | 6. Establishing a Retaining Wall, M.G. Weerathunga, 65° | 5 | 1 | 7.1538 | 80.3853 | 10 m x 3 m | Retaining Wall using stones | 2,000.00 m-2 | 60000 | 8335000 | Labour and other basic services by the Local community | 0.25 Years
9 | 954 | Uduwela waththa | 1. Development of five (05) Leader Drains | 1 | 1 | 7.25726, 7.25707, 7.25692 | 80.63435, 80.63318, 80.63315 | 12.5 km | Clearing and planting some trees along the banks (Areca nut) and other conservation practices |  | 1250000 |  | Labour and other basic services by the Local community/ Shramadana | 1 Year
|  |  |  | 5 | 2 | 7.15235, 7.15232 | 80.37582, 80.37579
|  |  |  | 1 | 3 | 7.1523 | 80.3815
|  |  |  | 3 | 4 | 7.1519 | 80.3832
|  |  |  | 1 | 5 | 7.1511 | 80.381
|  |  | 2. Establishment of Retaining Wall (Mr. Chaminda Wijekoon, Uduwelwatte), 70° | 4 | 1 | 7.1514 | 80.387 | 7 m x 6 m | Retaining Wall using stones | 2,000.00 m-2 | 84000 | 1334000 | Guidance by NRMC | 0.25 Years
10 | 955 | Galthenna | 1. Renovation of four (04) Leader Drains | 1 | 1 | 7.2568 | 80.6497 | 2.5 km | Clearing and planting some trees along the banks (Areca nut) and other conservation practices |  | 250000 |  | Labour and other basic services by the Local community/ Shramadana | 1 Year
|  |  |  | 1 | 2 | 7.2555 | 80.6478
|  |  |  | 1 | 3 | 7.255 | 80.6479
|  |  |  | 1 | 4 | 7.1524 | 80.3842
|  |  | 2. Establishing a Retaining Wall for Gorakagahamadithtgha Ela | 1 | 1 | 7.1512 | 80.3855 | 16 m x 4 m | Retaining Wall using stones | 2,000.00 m-2 | 128000 |  | Guidance by NRMC | 0.25 Years
|  |  | 3. Establishing a Retaining Wall 2 (Galthenne Junior School) | 5 | 1 | 7.15226, 7.15226 | 80.38436, 80.38437 | 22 m x 2 m | Retaining Wall using stones | 2,000.00 m-2 | 88000 |  | Funds by the Project | 0.25 Years
|  |  | 4. Soil and water conservation measures in Home Gardens/Galthenna, 55° | 3 | 1 | 7.15243, 7.15253 | 80.38408, 80.38466 | 12.5 ha | Live fencing/SALT Stone terracing/lock and spills, as applied | 250.00 m-1 | 3125000 | 3591000 | Labour and other basic services by the Local community | 0.5 Years
11 | 962 | Nehiniwela | 1. Rennovation of eleven (11) Leader Drains | 5 | 1 | 7.1513 | 80.3956 | 16.7 km | Clearing and planting some trees along the banks (Areca nut) and other conservation practices |  | 1670000 |  | Labour and other basic services by the Local community/ Shramadana | 1.5 Years
|  |  |  | 4 | 2 | 7.2528 | 80.6669
|  |  |  | 4 | 3 | 7.2536 | 80.6651
|  |  |  | 5 | 4 | 7.1518 | 80.4062
|  |  |  | 5 | 5 | 7.14574, 7.24914 | 80.40758, 80.66873
|  |  |  | 2 | 6 | 7.151 | 80.3957
|  |  |  | 1 | 7 | 7.1524 | 80.4044
|  |  |  | 1 | 8 | 7.1519 | 80.4027
|  |  |  | 3 | 9 | 7.1521 | 80.4016
|  |  |  | 1 | 10 | 7.2553 | 80.6695
|  |  |  | 3 | 11 | 7.2559 | 80.6701
|  | 3 | 2. Soil and water conservation measures in home gardens, Nahiniwela, 70 - 80° slope | 4 | 1 | 7.25037, 7.15344, 7.25135, 7.15126, 7.15179 | 80.66929, 80.40057, 80.66653, 80.39549, 80.40689 | 16 ha | Live fencing/SALT | 250.00 m-1 | 4000000 |  | Labour and other basic services by the Local community | 1 Year
|  |  | 3. Soil and water conservation measures in waste lands, Nahiniwela, 80° slope | 4 | 1 | 7.2506 | 80.6687 | 3 ha | Live fencing/SALT Stone terracing/lock and spills, as applied | 250.00 m-1 | 1200000 |  | Labour and other basic services by the Local community | 0.5 Years
|  |  | 4. Preparation of Drain at the middle of village/Raod, Nehiniwela | 4 | 1 | 7.2507 | 80.6675 | 1.5 km x 0.5 m x 0.5 m | Drain | 400.00 m-1 | 150000 |  |  | 0.25 Years
|  |  | 5. Soil and water conservation measures, Dewagolla Waththa (30 - 60°) | 4 | 1 | 7.1524 | 80.4091 | 24 ha | Live fencing/SALT - 15 ha Stone terracing - 5 ha Lock and Spills - 4 ha | 250.00 m-1 2,500.00 m-1 400.00 m-1 | 3750000 12500000 1600000 | 24870000 | Labour and other basic services by the Local community | 2 Years
12 | 963 | Godampitiya | 1. Stream bank conservation with side walls in Thalathuoya 1 | 3 | 1 | 7.2534 | 80.6693 | 0.5 km x 3 m 2 km | Side walls Clearing and planting some trees along the banks (Areca nut) and other conservation practices | 2,000.00 m-3 | 3000000 200000 |  | Labour and other basic services by the Local community/ Shramadana | 0.5 Years
|  |  | 2. Stream bank conservation with side walls in Thalathuoya 2 | 5 | 1 | 7.2529 | 80.6725 | 0.2 km x 6 m x 1 m | Side walls | 2,000.00 m-3 | 2400000 |  | Guidance by NRMC | 0.25 Years
|  |  | 3. Rennovation of Leader Drain 1 | 3 | 1 | 7.725 | 80.674 | 2 km | Clearing and planting some trees along the banks (Areca nut) and other conservation practices |  | 200000 |  | Labour and other basic services by the Local community/ Shramadana | 0.5 Years
|  |  | 4. Rennovation of Leader Drain 2 | 4 | 1 | 7.2498 | 80.6754 | 1.2 km | Clearing and planting some trees along the banks (Areca nut) and other conservation practices |  | 120000 |  | Labour and other basic services by the Local community/ Shramadana | 0.5 Years
|  |  | 5. Rennovation of Leader Drain 3 | 3 | 1 | 7.2498 | 80.6756 | 2 km | Clearing and planting some trees along the banks (Areca nut) and other conservation practices |  | 200000 | 6120000 | Labour and other basic services by the Local community/ Shramadana | 0.5 Years
13 | 964 | Puliyadda | 1. Renovation of three (03) Leader Drains | 2 | 1 | 7.1437 | 80.3922 | 5 km | Clearing and planting some trees along the banks (Areca nut) and other conservation practices |  | 500000 |  | Labour and other basic services by the Local community/ Shramadana | 0.5 Years
|  |  |  | 1 | 2 | 7.2415 | 80.6547
|  |  |  | 4 | 3 | 7.2377 | 80.6579
|  |  | 2. Establishment of Leader Drain/Uranhervuma Ela | 1 | 1 | 7.2407 | 80.391 | 0.3 km x 1 m x 1 m | Leader Drain | 3,000.00 m-3 | 900000 |  | Guidance by NRMC | 0.25 Years
|  |  | 3. Soil and water conservation measures in Puliyadda H.M.K.B. Herath and others, 45° | 1 | 1 | 7.14350, 7.14152, 7.14131 | 80.39255, 80.39257, 80.39257 | 16 ha | Live fencing/SALT Stone terracing/lock and spills, as applied | 250.00 m-1 | 4000000 |  | Funds by the Project | 0.5 Years 0.5 Years
|  |  | 4. Soil and water conservation measures in Hedansak Estate (30 - 60°) | 1 | 1 | 7.2365 | 80.4546 | 2.5 ha 4 ha | Lock and Spills Live fencing/SALT | 400.00 m-1 250.00 m-1 | 2.5*1000*400 1000000 | 6400000 |  | 0.25 Years
14 | 966 | Ethulgama West | 1. Rennovation of five (05) Leader Drains | 1 | 1 | 1027045, 1027088, 1027121 | 6244636, 6244593, 6244573 | 9 km | Clearing and planting some trees along the banks (Areca nut) and other conservation practices |  | 900000 |  | Labour and other basic services by the Local community/ Shramadana | 1.5 Years
|  |  |  | 5 | 2 | 1027076, 1027101 | 6244680, 6244652
|  |  |  | 2 | 3 | 1027141, 1027270 | 6244684, 6244591
|  |  |  | 3 | 4 | 1027188, 1027220 | 6244738, 6244622
|  |  |  | 4 | 5 | 1027049, 1027171, 1027280, 1027334 | 6244982, 6244788, 6244759, 6244678
|  |  | 2. Establishing a Retaining Wall 1 (Ingurugolla New) | 1 | 1 | 1027084 | 6244608 | 100 m x 3 m | Retaining Wall using stones | 2,000.00 m-2 | 600000 |  | Guidance by NRMC | 0.5 Years
|  |  | 3. Establishing a Retaining Wall 2 (Wehigaldeniya Ela and Kumbura) | 1 | 1 | 1027241 | 6244385 | 200 m x 3 m | Retaining Wall using stones | 2,000.00 m-2 | 1200000 |  | Funds by the Project | 0.5 Years
|  |  | 4. Soil and water conservation measures in Ingurugolla Watte (35°) | 2 | 1 | 1027087 | 6244902 | 1 ha | Stone terracing Live fencing/SALT | 2,500.00 m-1 250.00 m-1 | 2500000 250000 |  |  | 0.5 Years
|  |  | 5. Soil and water conservation measures (Ingurugolla New) (35 - 70°) | Needed | 1 | Scattered |  | 8 ha | Lock and spills - 3 ha Stone terracing - 2 ha Live fencing/SALT - 3 ha | 400.00 m-1 2,500.00 m-1 250.00 m-1 | 1200000 5000000 750000 |  | Labour and other basic services by the Local community | 0.5 Years
|  |  | 6. Soil and water conservation measures (Ingurugolla Old) (35 - 70°) | Needed | 1 | Scattered |  | 4 ha | Stone terracing - 2 ha Live fencing/SALT - 2 ha | 2,500.00 m-1 250.00 m-1 | 5000000 500000 |  | Labour and other basic services by the Local community | 0.25 Years
|  |  | 7. Soil and water conservation measures (Wehigaldeniya Ihalawatte) (35 - 70°) | Needed | 1 | Scattered |  | 16 ha | Stone terracing - 3 ha Live fencing/SALT - 10 ha Lock and spills - 3 ha | 2,500.00 m-1 250.00 m-1 400.00 m-1 | 7500000 2500000 1200000 | 27900000 | Labour and other basic services by the Local community | 1.5 Years
15 | 967 | Ethulgama North | 1. Rennovation of eight (08) Leader Drains | 4 | 1 | 1025896 | 6244636 | 29 km | Clearing and planting some trees along the banks (Areca nut) and other conservation practices |  | 2900000 |  | Labour and other basic services by the Local community/ Shramadana | 1.5 Years
|  |  |  | 4 | 2 | 1025882 | 6244489
|  |  |  | 2 | 3 | 1026336 | 6244399
|  |  |  | 2 | 4 | 1026493 | 6244361
|  |  |  | 2 | 5 | 1026732 | 6244307
|  |  |  | 2 | 6 | 1026758 | 6244365
|  |  |  | 1 | 7 | 1027064 | 6244338
|  |  |  | 1 | 8 | 1027191 | 6244317
|  |  | 2. Retaining Wall (Nikalanda Well) | 2 | 1 | 1026727 | 6244361 | 25 m x 4 m | Retaining Wall using stones | 2,000.00 m-2 | 200000 |  | Guidance by NRMC | 0.25 Years
|  |  | 3. Soil and water conservation/Overall (35 - 70°) | Needed | 1 | Scattered |  | 8 ha | Lock and spills - 2 ha | 400.00 m-1 | 800000 |  | Funds by the Project | 0.5 Years
[9 empty] | Stone terracing - 2 ha | 2,500.00 m-1 | 5000000
[9 empty] | Live fencing/SALT - 4 ha | 250.00 m-1 | 1000000 | 9900000
[9 empty] | Grand Total |  | 120777500 | 120777500