## Sheet1
Table 6 21: Time frame for implementation of minor irrigation proposals
Implementation Activity | Duration (Months)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Surveying, Design & Estimation for Minor Irrigation schemes
Ratification for proposals
Procurement procedure and selection of a contractor
Mobilization & procurement of material and equipment
Surveying Levelling and Setting out work
Construction
Quality Assurance
Certificate of Completion, Taking Over & Settlement of Payments