## Sheet1
Table 6 9: Implementation schedule of three tanks in MWS 008-2
Item | Duration (Months)
| 2 | 4 | 6 | 8 | 10
Survey, Investigation, and Estimation
Awareness and planting material selection
Procurement and awarding
Desilting, Planting of seedlings and maintaining