## Sheet1
Table 6 19: Time frame for implementing Stream Reservation Proposals
Implementation Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Survey & Estimation for reservation proposals
Public awareness and obtaining their concurrence for proposals
Procurement of necessary planting materials locally and out side
Vegetation & Construction activities
Public awareness on maintenance
Certificate of Completion, Taking Over & Settlement of payments